## Slide 1: Lessons learnt lecture #2
A look at scrutiny reviews
Maria Moriarty, Head of Resident Engagement and Corporate Experience
20 May 2021

## Slide 2: Lessons learnt lectures – the aim
Showcase learning opportunities as widely as possible so they can be applied to our day-to-day work.
Transparent by default – open session & post a video of the lecture, the slides and key learning points on our website.
Volunteers for future sessions to James.Mahaffy@networkhomes.org.uk
  Gabriel Codjoe June
No names of any individuals or organisations– otherwise everything is potentially in scope to maximise the learning potential.

## Slide 3: Structure
The story
The lessons
The learning
Questions/discussion

## Slide 4: The story
What is a scrutiny review and why do we do it?
Single Panel formed in 2016
First review – complaints escalating from stage 1 to 2
Objectives for the review were not set
Review lasted 14 months
Estimated cost of review £11,770
Notes: A scrutiny review is where we ask residents to undertake an independent review of our service. We are regulated by the Regulator of Social Housing and must adhere to their consumer and economic standards. One of the consumer standards is the Tenant Involvement and Empowerment standard which states we must "ensure that tenants are given a wide range of opportunities to influence and be involved in the scrutiny of their landlord's performance and the making of recommendations to the landlord about how performance might be improved." So while we are obligated to do it, it's also the right thing to do. Residents are the ones receiving the service we provide so are best placed to tell us what's working well and what's not working well offering us solutions to help us improve. Scrutiny provides residents with a chance to independently challenge us on our performance.
Prior to 2016 we had 2 Scrutiny Panels – one in London and one in Hertford. When we collapsed our structure to become Network Homes in 2016 we decided to have 1 panel to represent all residents and asked members of the existing panels if they’d like to be a part of it. We had 3 residents sign up from the Hertford panel and 4 from the London panel.
To bring the new panel together the RE team provided them with refresher training delivered by an external consultant. Following this training session the newly formed panel began their first scrutiny review looking at all repairs complaints escalating from stage 1 to stage 2 over the period of a year.
The panel decided against scoping out the scrutiny review and did not set any objectives as they wanted to see how it went as they worked their way through the review. They did not want any Network Homes staff members to be involved in the review but did agree for a colleague from the Governance team to minute their meetings. At the beginning of the review they agreed they would do any work required during the meeting only and arranged to meet every couple of months.
After 14 months the panel advised the RE team that they were ready to do their report. By that time only 2 residents remained on the panel. It took so long to get to that point that some of the committed residents had run out of enthusiasm and given up! During that time period there had also been many changes within Network. There had been a restructure to the RE Team and 2 staff left the team so the Resident Engagement Officer supporting the panel changed on a number of occasions. We had changed our Customer Relationship Management system (the system we use to log all interactions with residents) from 1View to CRM. Our main repairs contractor had changed. Many of the complaints the panel had reviewed would have related to a previous contractor.
When the final report was drafted some of the recommendations were no longer valid due to the changes I mentioned above or had already been addressed as a result of these changes and internal improvement mechanisms, such as better categorising the reason to log a complaint, had been put in place
The final report estimated the total cost of the review to be £11,770. This included staff costs, residents costs (in terms of them volunteering their time), resident expenses, printing, training, catering.
***
Estimated Total Cost of Complaints Scrutiny £11,770. Based on: · Combined Resident Hours – 80 hours per attendee · Combined Staff Hours – 380 @ avg £19/hour = £7220 · Catering - £350 · Resident Transport and Expenses - £3000* · Training - £1000 · Printing - £200

## Slide 5: The lessons
Communication
Set a clear structure for the scrutiny review
Be honest about what residents can influence and explain why there are things they might not be able to change
Establish a partnership between residents and staff with a common goal

## Slide 6: Communication
Be clear about the role
Personal issues
Running commentary during the review
Ensure better records of the review are maintained
Notes: Be clear to residents about the role:
The time commitment and work expected both inside and outside of meetings
The role profile, code of conduct and terms of reference for the panel.
Make sure they know that they shouldn’t bring up their own personal issues however can draw on these experiences
Make sure we keep residents up to date of any changes we are making that might impact on their review – for example during this review we:
Changed to a new software platform
Changed the complaints process and removed the complaints panel step within the process
Changed the categories of complaints on our system
Removed the automating of complaints on the system to avoid any issues.
We need to make sure we maintain better records (e.g electronic records, central locations of information and team updates on key milestones) during the review to ensure continuity of the project irrespective of any changes that might happen. If there are any staffing changes within the team this will mean that the review should be able to continue seamlessly.

## Slide 7: Set clear structure for the scrutiny review
Process
Scope
Timescales
Admin & support required
Notes: Be clear about the process for undertaking a successful review, ensuring sufficient training is delivered and that residents agree to adhere to the process
Make sure the review is fully scoped out with achievable objectives
Set clear timescales to avoid project drift
At the start of the review agree how the panel will operate:
  how often they’ll meet
  get the dates booked in
  once they’ve scoped out the review who will lead on the different areas
  what support they will need from the RE Team
  what other staff members they might want to speak to
  are there any other activities such as mystery shopping they might want to undertake
  who will write the final report.

## Slide 8: Be honest
Be clear about what they can influence
If there are things we are unable to change, make this clear
Notes: We should always be honest in our conversations with residents. Before they start on any scrutiny review we should be really clear about what the panel can influence and what they are not able to change…..and explain why they aren’t able to change something. For example if they are requesting system changes which may be exceed our budget we might need wot work with them to see how the recommendations can be implemented irrespective of system

## Slide 9: Partnership working
Common goal
Collaborative
Project team to Strengthen residents' trust in us
All colleagues need to be open to feedback
Notes: Everything we do when we engage with residents should be a partnership. To make the scrutiny review successful we need to agree a common goal so that we Network staff and the panel feel like one team.
We should be working together with residents to drive change and make improvements to the services we deliver to them. Everything we do should be collaborative.
A great example of where we’ve done this recently was when we developed our new objective: Strengthening residents’ trust in us. To develop this objective we set up a project team comprising 6 residents and 6 staff members who all worked together to bring this objective to life.
We all need to ensure we (and by that I mean everyone here at Network) are open to feedback. Often I find when feedback is offered we sometime see it as personal criticism rather than feedback about the service we are delivering.

## Slide 10: The learning – what we will do
Training with TPAS
New structure for undertaking scrutiny reviews
Introduced clear role profiles, code of conduct and terms of reference
Feedback to the Local Panels, Customer Services Committee and other residents following each scrutiny review
Notes: We’ve already made some changes that we hope will improve future scrutiny reviews. Before we made any changes we brought in TPAS (the Tenant Participation Advisory Service) to provide us with training around scrutiny, give us ideas on what we could do differently and train us to train others. We discussed the new process we were considering with them and incorporated their feedback.
Following this session we set up a new structure with 2 panels (one in Hertford and one in London) but rather than call them Scrutiny Panels, we now call them Continuous Improvement Panels. A couple of years ago we undertook a programme of delivering resident engagement workshops to all our colleagues. When we were explaining the importance of scrutiny during one particular session one of our colleagues asked us if we had to use this word because he thought it sounded quite negative. So when we started recruiting residents to these new panels we asked them what they thought we should call the panel and one of them suggested the Continuous Improvement Panel. This sounds much more positive and encompasses the purpose of undertaking scrutiny which is to make sure we are conintually improving our services to residents.
The CIP are responsible for:
Commissioning scrutiny
Overseeing the groups who undertake the scrutiny
Holding us to account to make sure we implement the recommendations that were agreed.
The biggest change was to move away from the panel itself undertaking the scrutiny. The membership of each panel is only 12 residents but we have 22,000 homes. So to hear the voices of more residents we decided to recruit residents to each individual review. This should enable us to hear from many more residents and may encourage greater numbers of residents to get involved because it will require less of a time commitment from them and it might be a topic that is of more interest to them.
There will be 2 types of groups:
Task & Finish Groups – who undertake scrutiny within 12-16 weeks
Sprint Groups – who undertake scrutiny within 2 days
We’ve produced very clear role profiles, code of conduct and terms of reference for the panels. And we deliver training to all residents being very clear what is expected from the role and how much time they will need to commit. We also ensure they know that we truly want their views to make a difference to our services and will work together with them to achieve this goal.
After each scrutiny review we'll make sure we report back to the CIP, the Local Panels, the Customer Services Committee and to all other residents as well.
There are various cultural activites and ongoing enphasis on engagement with residents, learning from their feedback and making changes as a result which makes me feel confident we would never have a situation like this again. And although we had already made changes as a result of it, coming to this session today has again pushed me to review it to see if there is anythiing else we could learn. I'm hoping that all of you may have some other ideas that you can share with me now.

## Slide 11: Questions & discussion